## 🗺️ Master Roadmap
PRODUCTION-GRADE RAG SYSTEM — 32-HOUR IMPLEMENTATION ROADMAP
Saturday 7hrs + Sunday 10hrs + Mon–Fri 3hrs/day = 32 Hours Total ¦ Target: Production RAG by Next Friday
Day | Session | Phase | Task | Theory Section | Library / Tool | Implementation File | Test / Checkpoint | Hours | Priority | Status | Notes | Blocker? | Done ✓
Saturday | 09:00–09:30 | Phase 0: Orient | Read §6 Why RAG Exists + §7 Full Pipeline from Theory Doc | §6, §7 | — | — | Can draw the full RAG pipeline from memory | 0.5 | CRITICAL | Not Started | Do not skip. Context for everything. | No | ☐
| 09:30–10:30 | Phase 1: Infra | docker compose up + pip install all deps + ollama pull models | N/A | docker, ollama, pip | docker-compose.yml, requirements.txt | All health checks green: postgres, qdrant, redis, minio, ollama | 1 | CRITICAL | Not Started | Do tonight if possible | No | ☐
| 10:30–11:00 | Phase 0: Orient | Read §2 Tokenization + §9 Chunking Theory | §2, §9 | — | — | Understand WHY chunking matters more than model choice | 0.5 | HIGH | Not Started | Key insight: bad chunk = bad everything | No | ☐
| 11:00–12:00 | Phase 2: Parse | Implement PDFParser (pdfplumber, table extraction) | §8 | pdfplumber | src/ingestion/parsers/pdf_parser.py | Parse a real PDF → print sections → no mid-sentence cuts, tables complete | 1 | CRITICAL | Not Started | Test with YOUR actual documents | No | ☐
| 12:00–13:00 | Phase 2: Parse | Implement SmartChunker (sentence boundary, table safety) | §9 | tiktoken | src/ingestion/chunking/smart_chunker.py | Print chunks: every table complete, every chunk has heading prefix | 1 | CRITICAL | Not Started | This is the most important hour of the whole weekend | No | ☐
| 13:00–13:30 | Phase 0: Orient | Read §3 Embeddings Theory (geometry of meaning) | §3 | — | — | Understand cosine similarity geometrically | 0.5 | HIGH | Not Started | Internalize before embedding code | No | ☐
| 13:30–14:00 | Phase 3: Embed | DenseEmbedder + manual cosine similarity test | §3, §10 | langchain-ollama | src/ingestion/embedding/dense_embedder.py | Embed 2 similar chunks → high similarity. Embed 1 unrelated → low similarity | 0.5 | CRITICAL | Not Started | Feel the geometry of meaning | No | ☐
| 14:00–14:30 | Phase 3: Embed | SparseEmbedder (FastEmbed SPLADE) + inspect output | §13 | fastembed | src/ingestion/embedding/sparse_embedder.py | Print sparse vector: {token_id: weight} — content words should have high weights | 0.5 | HIGH | Not Started | Verify stopwords get low weights | No | ☐
| 14:30–15:00 | Phase 3: Qdrant | Create Qdrant collection (named vectors + payload indexes) | §11 | qdrant-client | src/db/qdrant/collection.py | localhost:6333/dashboard shows empty collection with correct schema | 0.5 | CRITICAL | Not Started | Create ALL payload indexes before inserting data | No | ☐
| 15:00–15:30 | Phase 0: Orient | Read §13 BM25 + §14 Dense + §15 Hybrid/RRF theory | §13, §14, §15 | — | — | Work through RRF formula manually with paper and pen | 0.5 | HIGH | Not Started | Understand WHY RRF uses ranks not scores | No | ☐
| 15:30–16:30 | Phase 3: Qdrant | QdrantWriter upsert + HybridSearcher | §15 | qdrant-client | src/db/qdrant/writer.py, src/retrieval/hybrid_searcher.py | Search returns ranked chunks with rrf_score. Verify ordering makes sense. | 1 | CRITICAL | Not Started | Open Qdrant dashboard → see your first points | No | ☐
| 16:30–17:00 | Phase 3: DB | PostgreSQL hydration (batch SELECT by chunk_id array) | §15 | asyncpg | src/retrieval/pg_hydrator.py | SELECT returns full text + metadata for Qdrant result IDs. Order preserved. | 0.5 | CRITICAL | Not Started | Saturday exit: PDF searchable end-to-end | No | ☐
Sunday | 09:00–09:30 | Phase 0: Orient | Read §22 Agents + §23 LangGraph theory | §22, §23 | — | — | Draw state machine on paper before coding it | 0.5 | HIGH | Not Started | Key insight: nodes transform state, edges connect them | No | ☐
| 09:30–10:30 | Phase 4: Graph | RAGState TypedDict + LangGraph nodes (analyze, retrieve, generate) | §23 | langgraph | src/reasoning/state.py, src/reasoning/engine.py | First end-to-end query returns an answer with citations | 1 | CRITICAL | Not Started | Use LangGraph Studio to visualize the graph | No | ☐
| 10:30–11:00 | Phase 4: Graph | Conditional routing (simple → direct, complex → multi-agent) | §23 | langgraph | src/reasoning/engine.py | Simple query routes to DirectGen. Complex to MultiAgent. | 0.5 | HIGH | Not Started | Test with one simple and one complex query | No | ☐
| 11:00–11:30 | Phase 0: Orient | Read §25 Hallucination types + §26 Validation theory | §25, §26 | — | — | Identify all 4 hallucination types. Know which the Auditor catches. | 0.5 | HIGH | Not Started | Internalize before validation code | No | ☐
| 11:30–12:30 | Phase 5: Validate | Auditor + Gatekeeper LLM validators | §26 | langchain-ollama | src/validation/auditor.py, src/validation/gatekeeper.py | Deliberately trigger a hallucination → Auditor must flag it | 1 | CRITICAL | Not Started | Deliberate failure testing is the best learning here | No | ☐
| 12:30–13:00 | Phase 5: Validate | Wire validation into LangGraph + feedback loop (replan on fail) | §26 | langgraph | src/reasoning/engine.py | Failed validation → system replans → second attempt → improved answer | 0.5 | HIGH | Not Started | Max 2 retries to avoid infinite loops | No | ☐
| 13:00–13:30 | LUNCH | Break | — | — | — | — | 0.5 | — | — | — | No | —
| 13:30–14:00 | Phase 0: Orient | Read §19 Prompt Engineering for RAG | §19 | — | — | Apply citation-forcing prompt pattern to generate() node | 0.5 | HIGH | Not Started | Copy the system prompt template into your code | No | ☐
| 14:00–15:30 | Phase 6: Agents | Multi-agent: Retriever + Reasoner + Verifier agents | §22 | langgraph | src/agents/retriever_agent.py, reasoner_agent.py, verifier_agent.py | Complex comparative question → see each agent's contribution in state | 1.5 | HIGH | Not Started | Agents share state via LangGraph, not direct calls | No | ☐
| 15:30–16:00 | Phase 0: Orient | Read §27 RAGAS metrics (faithfulness algorithm specifically) | §27 | — | — | Understand: faithfulness = supported_claims / total_claims | 0.5 | HIGH | Not Started | Critical: this is your quality north star metric | No | ☐
| 16:00–17:00 | Phase 7: API | FastAPI endpoints: POST /documents, POST /query/sync, GET /health | N/A | fastapi, uvicorn | src/api/main.py, src/api/routers/documents.py, queries.py | curl POST /query/sync returns cited JSON response | 1 | HIGH | Not Started |  | No | ☐
| 17:00–17:30 | Phase 8: Eval | Build 10-pair golden dataset + run RAGAS evaluate() | §27 | ragas | tests/golden_dataset/qa_pairs.json, src/evaluation/runner.py | faithfulness > 0.75 AND answer_relevancy > 0.70 → proceed. Else: fix chunking. | 0.5 | CRITICAL | Not Started | If scores low: fix chunking FIRST, then rerun | No | ☐
| 17:30–18:00 | Phase 9: Lifecycle | soft_delete + update_metadata (PG + Qdrant payload) | §16 v2 doc | qdrant-client, asyncpg | src/db/qdrant/lifecycle.py | Delete doc → verify points gone from Qdrant dashboard. Update dept → search filters work. | 0.5 | HIGH | Not Started |  | No | ☐
| 18:00–19:00 | Phase 9: Lifecycle | version_bump + Celery async ingestion + Flower monitor | §14 v1 doc | celery, redis | src/workers/tasks.py, celery_app.py | Upload PDF → job_id returned → status goes pending→done. Flower shows task. | 1 | HIGH | Not Started | Sunday exit: full system working, RAGAS measured | No | ☐
Monday | 3hrs | Phase 10: Rerank | Read §16 Rerankers (full comparison). Install FlashRank. Wire into LangGraph. | §16 theory | flashrank | src/retrieval/reranker.py | Run 10 golden Q&A: record RAGAS BEFORE and AFTER reranker. Measure delta. | 1 | HIGH | Not Started | Target: context_precision improves ≥5% | No | ☐
| 3hrs | Phase 10: Rerank | Implement HyDE (generate hypothetical answer → embed → search) | §17 theory | langchain-ollama | src/retrieval/hyde.py | On 3 queries where regular search struggled: did HyDE find better chunks? | 1 | MEDIUM | Not Started | Adds ~500ms. Only enable for complex queries. | No | ☐
| 3hrs | Phase 10: Rerank | Lost-in-middle fix: reorder context (best first AND last) | §5 theory | Custom | src/reasoning/context_assembler.py | Rerun 10 golden pairs with new ordering. Record faithfulness delta. | 1 | HIGH | Not Started | Simple change, often 5-10% gain | No | ☐
Tuesday | 3hrs | Phase 2: Parse+ | DOCX parser (python-docx, heading hierarchy H1/H2/H3) | §8 theory | python-docx | src/ingestion/parsers/docx_parser.py | Parse a Word doc → headings preserved → chunks prefixed correctly | 1 | HIGH | Not Started |  | No | ☐
| 3hrs | Phase 2: Parse+ | HTML parser (bs4, filter nav/footer/ads) | §8 theory | beautifulsoup4 | src/ingestion/parsers/html_parser.py | Parse a saved webpage → navigation stripped → content preserved | 1 | MEDIUM | Not Started |  | No | ☐
| 3hrs | Phase 2: Parse+ | FileRouter (MIME type detection) + end-to-end test all types | §8 theory | python-magic | src/ingestion/parsers/file_router.py | Upload PDF, DOCX, HTML → all correctly parsed and indexed | 1 | HIGH | Not Started |  | No | ☐
Wednesday | 3hrs | Phase 11: Safety | Read §28 Red Teaming. Add instruction barrier to system prompt. | §28 theory | Custom prompt | src/core/prompts.py | 5 prompt injection tests: all blocked by [UNTRUSTED] prompt barrier | 1 | HIGH | Not Started |  | No | ☐
| 3hrs | Phase 11: Safety | RedTeamRunner: all 3 categories (injection, evasion, bias) | §28 theory | Custom | src/stress_testing/red_team.py | Run all 11 tests. Record pass/fail per category. >80% pass rate target. | 1 | HIGH | Not Started |  | No | ☐
| 3hrs | Phase 6: Agents+ | Query decomposition: LLM splits complex queries → sub-queries → union results | §20 theory | langgraph | src/reasoning/planner.py | "Compare X vs Y" → 2 sub-queries → 2 retrievals → synthesized comparison | 1 | MEDIUM | Not Started |  | No | ☐
Thursday | 3hrs | Phase 8: Eval+ | Expand golden dataset to 30 pairs (10 factual, 10 comparative, 10 procedural) | §27 theory | ragas | tests/golden_dataset/qa_pairs.json | RAGAS on all 30. Break down scores by query type. Identify weakest. | 1 | CRITICAL | Not Started | This is your evidence base for all future improvements | No | ☐
| 3hrs | Phase 8: Eval+ | Qdrant fusion_gain metric (dense_recall vs sparse_recall vs hybrid_recall) | §27 theory | qdrant-client | src/evaluation/qdrant_metrics.py | fusion_gain > 0.05 → sparse is contributing. Else: check SPLADE tokenization. | 1 | HIGH | Not Started |  | No | ☐
| 3hrs | Phase 8: Eval+ | Fix the lowest RAGAS metric. Change ONE thing. Re-run. Verify improvement. | §27 theory | Depends on metric | Depends on finding | Metric improves by measurable amount after change. Document what you changed and why. | 1 | CRITICAL | Not Started | This IS production RAG engineering discipline | No | ☐
Friday | 3hrs | Phase 12: Observe | Read §31 Latency. Time every LangGraph node. Build p50/p95 table. | §31 theory | structlog, time | src/core/logging.py | JSON log per node: duration_ms. p95 < 3500ms total. | 1 | HIGH | Not Started |  | No | ☐
| 3hrs | Phase 12: Observe | QdrantReconciler: verify PG ↔ Qdrant sync. Fix any drift. | §16 v2 doc | qdrant-client | src/db/qdrant/reconciler.py | Reconciler output: chunks_unsynced = 0 | 1 | HIGH | Not Started |  | No | ☐
| 3hrs | Phase 13: Final | End-to-end integration test: new PDF → 5 queries (factual/compare/procedural/edge/adversarial) → RAGAS | All | All | tests/integration/test_e2e.py | All 5 queries return cited answers. RAGAS faithfulness > 0.80. 1 red team test passes. | 1 | CRITICAL | Not Started | This is your production readiness gate | No | ☐
TOTAL PLANNED HOURS

## 📊 Daily Status
DAILY STATUS & METRICS TRACKER
Day | Budget (hrs) | Focus | Tasks Completed | Tasks Total | Completion % | RAGAS Faithfulness | RAGAS Relevancy | Latency p95 (ms) | Notes / Blockers
Saturday | 7 | Infrastructure + Parser + Chunker + Dual Embed + Qdrant Collection + Hybrid Search | 0 | 12
Sunday | 10 | LangGraph Engine + Validation Layer + Multi-Agent + FastAPI + RAGAS + Lifecycle | 0 | 12
Monday | 3 | Reranker (FlashRank) + HyDE + Lost-in-Middle context ordering | 0 | 3
Tuesday | 3 | DOCX Parser + HTML Parser + FileRouter + multi-format end-to-end test | 0 | 3
Wednesday | 3 | Red Teaming + Prompt Injection Defense + Query Decomposition | 0 | 3
Thursday | 3 | Expand golden dataset to 30 + RAGAS full suite + Qdrant fusion_gain metric | 0 | 3
Friday | 3 | Latency profiling + Reconciler + Final integration test (production gate) | 0 | 3
|  | >0.80 | >0.70 | >0.75 | >0.75 | >0.05 | <3500 |  | All tests pass

## ✅ Checklists
PRODUCTION READINESS CHECKLISTS
SATURDAY EXIT CRITERIA
☐ | PDF parsed with tables intact | pdfplumber | Not Started
☐ | SmartChunker: no mid-sentence cuts | tiktoken | Not Started
☐ | SmartChunker: every table = 1 chunk | Custom | Not Started
☐ | Chunks have section_heading prefix | Custom | Not Started
☐ | Dense embedding cosine similarity test passed | nomic-embed-text | Not Started
☐ | Sparse embedding: stopwords have low weights | FastEmbed SPLADE | Not Started
☐ | Qdrant collection visible at localhost:6333/dashboard | qdrant-client | Not Started
☐ | Qdrant payload indexes created (dept, is_latest, date) | qdrant-client | Not Started
☐ | Hybrid search returns ranked results (rrf_score present) | Qdrant RRF | Not Started
☐ | PostgreSQL hydration returns full text for chunk_ids | asyncpg | Not Started
☐ | End-to-end: query → ranked cited chunks returned | All | Not Started
SUNDAY EXIT CRITERIA
☐ | LangGraph state machine compiles without errors | langgraph | Not Started
☐ | analyze → retrieve → generate → END flow works | langgraph | Not Started
☐ | Conditional routing: simple vs complex detected correctly | langgraph | Not Started
☐ | Auditor catches deliberately hallucinated claim | LLM validator | Not Started
☐ | Gatekeeper catches off-topic response | LLM validator | Not Started
☐ | Validation failure → replan → improved second answer | langgraph | Not Started
☐ | Multi-agent: Retriever + Reasoner + Verifier all activate | langgraph | Not Started
☐ | FastAPI POST /query/sync returns cited JSON | fastapi | Not Started
☐ | RAGAS faithfulness > 0.75 on 10 golden pairs | ragas | Not Started
☐ | RAGAS answer_relevancy > 0.70 | ragas | Not Started
☐ | Soft delete: Qdrant points disappear from dashboard | qdrant-client | Not Started
☐ | Metadata update: dept filter works after payload update | qdrant-client | Not Started
☐ | Celery async ingestion: job_id → status polling works | celery | Not Started
☐ | Flower shows completed ingestion task | flower | Not Started
WEEKDAY COMPLETION GATES
☐ | FlashRank reranker: context_precision improves ≥5% | flashrank | Not Started
☐ | HyDE: tested on 3 queries where standard search struggled | Custom | Not Started
☐ | Context ordering (best first+last): faithfulness improves | Custom | Not Started
☐ | DOCX parser: heading hierarchy H1/H2/H3 preserved | python-docx | Not Started
☐ | HTML parser: nav/footer/ads stripped correctly | beautifulsoup4 | Not Started
☐ | FileRouter: PDF + DOCX + HTML all correctly detected | python-magic | Not Started
☐ | 5 prompt injection tests: all blocked | System prompt | Not Started
☐ | 3 info evasion tests: all blocked | System prompt | Not Started
☐ | 3 bias tests: no discriminatory outputs | Validation | Not Started
☐ | Query decomposition: comparative query → 2 sub-retrievals | langgraph | Not Started
☐ | Golden dataset expanded to 30 Q&A pairs | ragas | Not Started
☐ | RAGAS faithfulness > 0.80 on 30-pair dataset | ragas | Not Started
☐ | fusion_gain > 0.05 (sparse is contributing) | qdrant-client | Not Started
☐ | Weakest metric identified and improved by measurable amount | ragas | Not Started
☐ | structlog: every LangGraph node logs duration_ms | structlog | Not Started
☐ | p95 total latency measured and < 3500ms | Custom | Not Started
☐ | Reconciler: chunks_unsynced = 0 | qdrant-client | Not Started
☐ | Integration test: 5 diverse queries all return cited answers | All | Not Started
☐ | FINAL: RAGAS faithfulness > 0.80 on unseen document | ragas | Not Started
☐ | FINAL: 1 red team adversarial test blocked | stress_testing | Not Started
PRODUCTION READINESS FINAL GATE
☐ | All ingestion lifecycle ops work: create/update/delete/version | lifecycle.py | Not Started
☐ | Qdrant reconciler runs and finds 0 unsynced chunks | reconciler.py | Not Started
☐ | System handles unseen document type gracefully | FileRouter | Not Started
☐ | API returns 4xx with clear message for bad inputs | fastapi | Not Started
☐ | Prompt injection returns refusal, not injected content | System prompt | Not Started
☐ | Faithfulness > 0.80 consistently across query types | ragas | Not Started
☐ | No unhandled exceptions in 10-query stress test | All | Not Started
☐ | Query audit trail stored in PostgreSQL queries table | asyncpg | Not Started
☐ | All Celery tasks have max_retries=3 and retry logic | celery | Not Started
☐ | Environment variables in .env (no hardcoded secrets) | pydantic-settings | Not Started

## 📈 RAGAS Metrics
RAGAS EVALUATION METRICS TRACKER — Track Every Run
Run # | Date | What Changed | Faithfulness | Answer Relevancy | Context Recall | Context Precision | Fusion Gain | p95 Latency (ms) | Notes
TARGET |  | Production Target | >0.80 | >0.70 | >0.75 | >0.75 | >0.05 | <3500
1 | Sunday | Baseline (no reranker, no HyDE, top_k=8) | [6 empty] | First measurement — establish baseline
2 | Monday | Added FlashRank reranker | [6 empty] | Expect context_precision to improve
3 | Monday | Added HyDE for complex queries | [6 empty] | Expect context_recall to improve
4 | Monday | Lost-in-middle context reordering | [6 empty] | Expect faithfulness to improve
5 | Thursday | Expanded to 30-pair golden dataset | [6 empty] | More reliable measurements
6 | Thursday | Fix applied to weakest metric | [6 empty] | Document what you changed
7 | Friday | Final production test on unseen document | [6 empty] | Production gate measurement

## 🔧 Tech Stack
COMPLETE TECHNOLOGY STACK REFERENCE
Category | Library / Tool | Version | Install Command | Used In | Purpose | Doc Link
Infrastructure | Docker Desktop | 4.x | choco install docker-desktop | All services | Container runtime for PG, Qdrant, Redis, MinIO | docs.docker.com
Infrastructure | PostgreSQL 16 | 16.x | Via docker-compose.yml | Relational data, audit | Source of truth for documents, chunks, queries | postgresql.org/docs
Infrastructure | Qdrant | latest | Via docker-compose.yml | Vector search | HNSW index, sparse vectors, RRF fusion | qdrant.tech/documentation
Infrastructure | Redis 7 | 7.x | Via docker-compose.yml | Celery broker | Task queue broker + result backend | redis.io/docs
Infrastructure | MinIO | latest | Via docker-compose.yml | Object storage | Raw document storage (S3-compatible) | min.io/docs
Infrastructure | Ollama | latest | ollama.com/download | LLM + Embeddings | Local LLM serving (llama3.2, nomic-embed) | ollama.com
API | FastAPI | 0.115.0 | pip install fastapi | HTTP layer | Async REST API, OpenAPI auto-docs, SSE streaming | fastapi.tiangolo.com
API | uvicorn | 0.30.6 | pip install uvicorn[standard] | ASGI server | Production ASGI server for FastAPI | uvicorn.org
Config | pydantic-settings | 2.5.2 | pip install pydantic-settings | core/config.py | .env loading with type validation | docs.pydantic.dev
Database | asyncpg | 0.29.0 | pip install asyncpg | db/postgres/ | Async PostgreSQL driver (fastest) | github.com/MagicStack/asyncpg
Database | SQLAlchemy[asyncio] | 2.0.35 | pip install sqlalchemy[asyncio] | db/models.py | ORM for PostgreSQL models + migrations | docs.sqlalchemy.org
Database | alembic | 1.13.3 | pip install alembic | alembic/ | Database schema migrations | alembic.sqlalchemy.org
Vector DB | qdrant-client | 1.11.0 | pip install qdrant-client | db/qdrant/ | Python SDK + gRPC for Qdrant operations | github.com/qdrant/qdrant-client
Embedding | fastembed | 0.3.6 | pip install fastembed | embedding/sparse_embedder.py | SPLADE sparse embeddings (local, ONNX) | github.com/qdrant/fastembed
Embedding | langchain-ollama | 0.2.0 | pip install langchain-ollama | embedding/dense_embedder.py | nomic-embed-text via Ollama (local dense) | python.langchain.com
Agents | langchain | 0.3.0 | pip install langchain | Throughout | LLM chains, prompts, tools framework | python.langchain.com
Agents | langgraph | 0.2.16 | pip install langgraph | reasoning/ | Stateful agent graph (state machine) | langchain-ai.github.io/langgraph
Agents | langchain-openai | 0.2.0 | pip install langchain-openai | core/llm_client.py | OpenAI LLM integration (optional) | python.langchain.com
Parsing | pdfplumber | 0.11.4 | pip install pdfplumber | parsers/pdf_parser.py | PDF text + table extraction with bbox | github.com/jsvine/pdfplumber
Parsing | python-docx | 1.1.2 | pip install python-docx | parsers/docx_parser.py | DOCX heading hierarchy + table extraction | python-docx.readthedocs.io
Parsing | beautifulsoup4 | 4.12.3 | pip install beautifulsoup4 | parsers/html_parser.py | HTML parsing, nav/footer stripping | crummy.com/software/BeautifulSoup
Parsing | unstructured | 0.15.14 | pip install unstructured[pdf,docx] | parsers/universal.py | Universal document parser fallback | unstructured.io
Chunking | tiktoken | 0.7.0 | pip install tiktoken | chunking/smart_chunker.py | Token counting (cl100k_base encoding) | github.com/openai/tiktoken
Metadata | keybert | 0.8.5 | pip install keybert | metadata/keyword_extractor.py | Keyword extraction from chunk text | github.com/MaartenGr/KeyBERT
Metadata | spacy | 3.7.5 | pip install spacy && python -m spacy download en_core_web_sm | reasoning/query_analyzer.py | NER for entity extraction in queries | spacy.io
Reranking | flashrank | 0.2.x | pip install flashrank | retrieval/reranker.py | Fast quantized cross-encoder reranker | github.com/PrithivirajDamodaran/FlashRank
Task Queue | celery[redis] | 5.4.0 | pip install celery[redis] | workers/ | Async task queue for ingestion jobs | docs.celeryq.dev
Task Queue | flower | 2.0.1 | pip install flower | Monitoring | Celery task monitoring web UI (port 5555) | flower.readthedocs.io
Storage | minio | 7.2.9 | pip install minio | storage/minio_client.py | MinIO S3-compatible Python SDK | min.io/docs/minio/linux/developers/python
Evaluation | ragas | 0.1.21 | pip install ragas | evaluation/ | RAG evaluation: faithfulness, relevancy, recall | docs.ragas.io
Observability | structlog | 24.4.0 | pip install structlog | core/logging.py | Structured JSON logging | structlog.readthedocs.io
LLM Models | llama3.2:8b | meta | ollama pull llama3.2:8b | All LLM calls | Fast local LLM (4.7GB RAM, good quality) | ollama.com/library/llama3.2
LLM Models | nomic-embed-text | nomic | ollama pull nomic-embed-text | Dense embeddings | Best local embedding model (274MB, 768-dim) | ollama.com/library/nomic-embed-text